PV(Solar) Construction Starting    September 11th     	   EXTREME PARKING RESTRICTIONS

We have just been informed that the construction of the PV(Solar Panel) system will begin on Monday September 11th.

We were given a list of parking restrictions based on the safety requirements and construction needs of the contractor. This is not in the control of the Pearlridge Square office. We are still working to find alternatives and we will be talking to the contractors after the weekend as well so there will be further notices and updates as they become available.

At this time(and this should not change) all stalls on the MAKAI side of the building(Pearl Harbor Side) must be empty by 8:00am on Monday September 11 when the steel beams will be moved onto the 3rd floor deck.

This includes stalls 371 through 399,

stalls 3A,3B,3C,3D,3E,3F,3G and rental stalls 1-9 and 23,24

On September 12 the actual construction begins and we've been told that there will be no access to those stalls or rental parking during the construction. The schedule as follows

11th: Delivery of Steel to site and crane to the deck, spread load around 3rd floor.

3rdFloor, Makai side, all clear of vehicles

12th– 14th Coring of Phase 1 and Column placement with cross members.

3rdFloor, Makai side, all clear of vehicles

2ndFloor, Phase 1 section all clear of vehicles(We will advise which stalls)

(PHASE 1 STALLS  are #371 through 392)

15th– 19th Coring of Phase 2 and Column placement with cross members.

3rdFloor, Makai side, Phase 1 section OPEN, Phase 2 section all clear of vehicles

2ndFloor, Phase 1 section OPEN, Phase 2 section all clear of vehicles.

(PHASE 2 STALLS 393 through 399 3A through 3G Rental stalls 1 through 10 and 23,24

20th– 25th  Contingency days should either Phase 1 or 2 or both encounter problems with construction.

GUEST PARKING WILL NOT BE AVAILABLE AT ALL ON THE 11th AND WILL AT BEST BE EXTREMELY LIMITED UNTIL THE 20th. PLEASE KEEP THIS IN MIND FOR ANY GUESTS OR CONTRACTORS. DO NOT ASSUME THERE WILL BE ANY GUEST PARKING DURING THIS TIME

***IF YOU WILL BE GONE DURING THIS TIME AND UNAVAILABLE TO MOVE YOUR VEHICLE AS REQUIRED PLEASE ADVISE THE OFFICE ASAP!!!!

This is allot of info but we wanted to make you aware of the situation ASAP. We will follow up with any new information as it becomes available.

Come by the office and see Dave or Kalani for any questions and we will assist you as best we can. Please understand that we are not in charge of this project and that all of these situations are determined by the safety and the desire to get this construction phase of the project completed as quickly and safely as possible.

We understand that this will be extremely inconvenient and appreciate your understanding. When it's done you will at least have covered parking

Mahalo,

Dave Zatal

Resident Manager